## Sheet1
Template ID | Task ID | Task Description | Predecessor Task | Responsible User | Task Type | Start Date | End Date
MC2025 | AP001 | Post Vendor Invoices | - | AP_USER | Manual | 2025-09-01 | 2025-09-01
MC2025 | AP002 | Run Invoice Accruals | AP001 | AP_USER | Program | 2025-09-02 | 2025-09-02
MC2025 | AP003 | Clear GR/IR Accounts | AP002 | AP_USER | Program | 2025-09-02 | 2025-09-02
MC2025 | AR001 | Apply Customer Receipts | - | AR_USER | Manual | 2025-09-01 | 2025-09-01
MC2025 | AR002 | Close AR Subledger | AR001 | AR_USER | Program | 2025-09-02 | 2025-09-02
MC2025 | AR003 | Intercompany Reconciliation - AR | AR002 | AR_USER | Manual | 2025-09-03 | 2025-09-03
MC2025 | PY001 | Post Payroll Journal | - | PAY_USER | Manual | 2025-09-02 | 2025-09-02
MC2025 | PY002 | Accrue Payroll Expenses | PY001 | PAY_USER | Program | 2025-09-03 | 2025-09-03
MC2025 | BK001 | Load Bank Statements | - | TREAS_USER | Program | 2025-09-01 | 2025-09-01
MC2025 | BK002 | Reconcile Bank Accounts | BK001 | TREAS_USER | Manual | 2025-09-03 | 2025-09-03
MC2025 | FA001 | Run Depreciation | - | FA_USER | Program | 2025-09-03 | 2025-09-03
MC2025 | FA002 | Post Asset Additions/Retirements | FA001 | FA_USER | Manual | 2025-09-03 | 2025-09-03
MC2025 | GL001 | Run Allocations | AP003, AR003, PY002, BK002, FA002 | GL_USER | Program | 2025-09-04 | 2025-09-04
MC2025 | GL002 | FX Revaluation | GL001 | GL_USER | Program | 2025-09-04 | 2025-09-04
MC2025 | GL003 | Post Manual Journals | GL002 | GL_USER | Manual | 2025-09-04 | 2025-09-04
MC2025 | CONS01 | Consolidation & Reporting | GL003 | FIN_MGR | Program | 2025-09-05 | 2025-09-06