## Artefact control sheet
Tower 6
Risk, Compliance & Audit Trail
Artefact control sheet
SL Number | Master Data & Analytics layer | Data Collection | File preparation | Completion | Expected Draft Completion Date | Review timeline | Artefact finalisation | Comment/ Current status
1 | Examples of SoD conflicts (e.g., JE posting + approval | Complete | Complete | Complete |  | 411145 | 2025-09-10 | Ready for review
2 | Remediation workflow | Complete | Complete | Complete |  | 411145 | 2025-09-10 | Ready for review
3 | Access control policy | In-progress | Not started | In-progress | 2025-08-29 | 2025-09-05 | 2025-09-17 | In-progress
4 | Automated control libraries (3-way match for accruals, JE validation rules) | In-progress | Not started | In-progress | 2025-08-29 | 2025-09-05 | 2025-09-17 | To start
5 | Control testing scripts (automated/manual) | In-progress | Not started | In-progress | 2025-09-05 | 2025-09-10 | 2025-09-24 | To start
6 | BlackLine or SAP control rule configuration examples | In-progress | Not started | In-progress | 2025-09-05 | 2025-09-10 | 2025-09-24 | To start
7 | SOX/ICFR control mapping to R2R processes | In-progress | Not started | In-progress | 2025-09-12 | 2025-09-17 | 2025-10-01 | To start
8 | Entity-level compliance scorecards | In-progress | Not started | In-progress | 2025-09-12 | 2025-09-17 | 2025-10-01 | To start
9 | Remediation tracking logs and self-assessment tools | In-progress | Not started | In-progress | 2025-09-19 | 2025-09-24 | 2025-10-06 | To start