## Artefact control sheet
Tower 1
Governance & Policy Framework
Artefact control sheet
SL Number | Master Data & Analytics layer | Data Collection | File preparation | Completion | Expected Draft Completion Date | Review timeline | Artefact finalisation | Comment/ Current status
1 | IFRS-to-local GAAP comparison charts | Complete | Complete | Complete |  | 411145 | 2025-09-10 | Ready for review
2 | IFRS-to-local GAAP country-level policy annexures | In-progress | In-progress | In-progress |  | 411145 | 2025-09-10 | To start
3 | Check compliance readiness (e.g., policies, controls) | In-progress | Not started | In-progress | 2025-09-01 | 2025-09-05 | 2025-09-17 | To start
4 | Policy Templates: JE policy, Close policy, Intercompany, FX policy, asset accounting, consolidation, COA, revenue accounting, Cost allocations | In-progress | In-progress | In-progress | 2025-08-29 | 2025-09-05 | 2025-09-17 | To start
5 | SOPs: Policy revision process, CoA maintenance SOP | In-progress | In-progress | In-progress | 2025-09-05 | 2025-09-10 | 2025-09-24 | To start
6 | Approval Flows: RACI charts, approval matrices for policy sign-off | In-progress | In-progress | In-progress | 2025-09-05 | 2025-09-10 | 2025-09-24 | To start