## Sheet1
Task ID | Task Description | Process | Owner | Dependency | Day | Status
AP001 | Post Vendor Invoices | AP | AP Manager | None | Day 0 | Pending
AR001 | Apply Customer Receipts | AR | AR Manager | None | Day 0 | Pending
PY001 | Post Payroll Journal | Payroll | Payroll Lead | None | Day 0 | Pending
BK001 | Load Preliminary Bank Statements | Treasury | Treasury Mgr | None | Day 0 | Pending
AP002 | Run Invoice Accruals | AP | AP Manager | AP001 | Day +1 | Pending
AP003 | Clear GR/IR Accounts | AP | AP Manager | AP001 | Day +1 | Pending
AR003 | Intercompany Reconciliation - AR | AR | AR Manager | AR001 | Day +1 | Pending
PY002 | Accrue Payroll Expenses | Payroll | Payroll Lead | PY001 | Day +1 | Pending
BK002 | Reconcile Bank Accounts | Treasury | Treasury Mgr | BK001 | Day +1 | Pending
FA001 | Run Depreciation | Fixed Assets | FA Lead | AP002, AR003 | Day +2 | Pending
GL001 | Run Allocations | GL | GL Accountant | AP002, AR003, PY002, BK002 | Day +2 | Pending
GL002 | FX Revaluation | GL | GL Accountant | GL001 | Day +2 | Pending
GL003 | Post Manual Journals | GL | GL Accountant | GL001 | Day +2 | Pending
CONS01 | Consolidation & Reporting | Consolidation | Group Ctrl | GL001, GL002, FA001 | Day +3 | Pending