## Project Plan_vRoadmap (hidden)
Raytheon (RTX) Cost Allocations Transformation - Phase 2
Activities | [6 empty] | Month 0 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
[7 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44
 | time axis 2025-02-03 to 2025-12-29
0. Engagement Administration and Economics |  | Owner | Wave | Start | End | Status
1 | Setup engagement in GEAR (incl. upload of SOW and MSA) | EY |  |  |  | Open
2 | Create SQ plan | EY |  |  |  | Open
3 | Review RTX Data Privacy requirements | EY |  |  |  | Open
4 | Update engagement win status | EY |  |  |  | Open
5 | Perform ETC #1 | EY |  |  |  | Open
6 | Execute internal kickoff | EY |  |  |  | Open
7 | Distribute invoice #1 | EY |  |  |  | Open
8 | Perform ETC #2 | EY |  |  |  | Open
9 | Perform ETC #3 | EY |  |  |  | Open
10 | Perform ETC #4 (if needed) | EY |  |  |  | Open
11 | Distribute invoice #2 | EY |  |  |  | Open
Phase 1 Extension |  | Owner |  | Start | End | Status
Define new driver data | [5 empty] | Open
| Create and Facilitate completion of template for new drivers to service owners | EY
| Create data collection template for all proposed drivers (e.g., calculations, level of detail, sources, owners, frequency) and share with service owners | EY |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Create base data catalog - including new data collected, forecast and actuals | EY |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Perform high level analysis of forecast to actuals to confirm predictability hypotheses | EY |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
Finalize and socialize Direct Charge decision Matrix | [5 empty] | Open
Create Direct Charge decision matrix
| Finalize Direct Charge decision matrix |  |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Evaluate direct charge cost pools with ES Finance (2nd round) |  |  | 2025-02-10 | 2025-02-21 | bar: 2025-02-10 to 2025-02-17
| Evaluate direct charge cost pools with OneRTX and Service Catalog teams |  |  | 2025-02-10 | 2025-02-21 | bar: 2025-02-10 to 2025-02-17
Support Socialization of Allocation Architecture | [5 empty] | Open
| Facilitate detailed reviews with stakeholders | EY
| Evaluate drivers with ES Finance (2nd Round) | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Evaluate drivers and cost pools with Government accounting team | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Evaluate drivers with ES Services owners | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Engage OneRTX team and Service Catalog team on cost categories in order to future proof drivers and pools | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Develop agenda and materials for BU outreach - cost pools, drivers, direct charge | EY |  | 2025-02-24 | 2025-02-28 | bar: 2025-02-24
Refine model, perform scenarios | [5 empty] | Open
| Refine high level cost impact model with new driver data | EY
| Iterate model to reflect new driver data | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Iterate model to reflect additional pressure tested scenarios | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Iterate model to reflect direct charge scenarios (omission of costs) | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Socialize high level impacts | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
TMO |  | Owner |  | Start | End | Status
Engagement Management |  | EY |  | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Transformation Management |  | EY |  | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Process | [5 empty] | Status
Standardize and Streamline ES Cost Allocation Process | [5 empty] | Open
| Direct charge process definition & design | EY | 1 | 2025-03-03 | 2025-04-18 | Open | bar: 2025-03-03 to 2025-04-14
| Map and define the current state direct charge allocation process (SIPOC) | EY
| Define direct charge criteria | EY
| Create direct charge process flows and procedures | EY
Develop comprehensive SOPs and training materials for updated processes
| Non-direct process definition & design | EY | 1 | 2025-04-21 | 2025-07-04 | Open | bar: 2025-04-21 to 2025-06-30
| Map and define the current state non-direct allocation process (SIPOC) | EY
Engage key subject matter resources to gather data on allocations requirements - remove should be captured in data/tech
Outline opportunities for standardization and streamlining within process
Test opportunity hypotheses for all non-direct allocations
| Design streamlined process incorporating upstream data collection and downstream reporting | EY
Refine allocation architecture to incorpoate Future ES scope
| Develop comprehensive SOPs and training materials for updated processes | EY
| Model and Implement non-direct charge changes to Brochure | RTX/EY
Host review workshops on final allocation architecture with key finance stakeholders (FPA, Controllership, ES, Gov Acct)
| Streamline upstream/downstream timely distribution to BUs for Non-Direct Process | RTX | 2 | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Identify current process for distribution and submission of brochure
Determine pain points and opportunities with adjustment of brochure distribution
Standardize communication procedures for receiving and submitting of brochure
Socialize standardized process for distribution of brochure to BUs
Compile all relevant data related to the non-brochure ES cost structure - move, should be covered in data/tech
Review the collected cost data to identify inconsistencies or discrepancies in how costs are allocated across different services - move, should be covered in data/tech somewhere
Re-align on Benchmark cost structure against industry standards and best practices
Develop and implement recommendations to enhance non-Brochure ES costs and the corresponding process structure - move, this should be tied to future opps around corp allocatiosn
Streamline consolidation and maintenance of cost centers | [5 empty] | Open
| Confirm future cost center structure | EY | 1 | 2025-08-18 | 2025-10-31 | Open | bar: 2025-08-18 to 2025-10-27
Evaluate opportunity for changes in cost center structure
Align with OneRTX, Service Catalog, and ES Finance
Develop guidelines and procedures for future state cost center structure
Socialize new guidelines for new cost center structure
Align cost centers to Service catalog (ideal state 3 cost centers per service)
| Execute changes in the system to consolidate and eliminate cost centers | RTX | 2 | 2025-08-18 | 2025-10-31 | Open | bar: 2025-08-18 to 2025-10-27
Conduct a comprehensive review of the current cost center structure and identify areas of improvement
Expand scope of assessment to include corporate costs (consistency check)
Develop standardized guidelines for establishing, consolidating, and maintaining cost centers; including guidelines for when new cost centers are added to the ES Brochure
Socialize new structure with ES stakeholders and outlines roles / responsibilities for maintaing cost centers
Test drivers based on statistical relationships (actuals v. forecast)
Develop documentation of cost center guidelines and maintenance and implement periodic reviews
Streamline layers of cost allocation from ES to receiving cost centers |  | EY | 3
Identify receiving cost centers and align drivers
| Evaluate driver data to lowest BU cost mapping level | EY
| Evaluate direct charge impact on BUs cost mapping | EY
Review draft cost mapping with ES Finance Leads & BU Leads
Review draft cost mapping with BU leads
Socialize refined driver data to BUs & ES Leads
Document opportunities to remove layers of cost allocation within CA and PW
Workshop new structure with ES functional leads and gather feedback
Workshop new structure with BU leads and gather feedback
Incorporate feedback from current process and develop future state process
Socialize standardized process for distribution of brochure to BUs
| Implement changes for brochure release | RTX
Update CAS statements (Government Accounting)
Identify cost accounting changes
Assess existing CHO, ES, IHO, and Segment CAS Disclosure Statements
Revise CAS disclosure statements
Update existing CHO, ES, IHO, and Segment CAS Disclosure Statements based on new allocation bases/drivers
Prepare forward pricing and provisional billing rate proposals
Provide BU’s with updated allocation data
Assist BU’s in the preparation of forward pricing and provisional billing rate proposals, as needed
Business Partnering | [5 empty] | Open
Enhance governance around incoming ES scope | [5 empty] | Open
| Document service catalog and cost structure mapping (e.g. cost centers map to which service area) | RTX | 1 | 2025-03-17 | 2025-06-06 | Open | bar: 2025-03-17 to 2025-06-02
Identify target service areas within each mission area
Establish service area mapping of cost pools
Develop documentation of new structure and mapping of cost pools within service areas
| Define guidance and process for incoming ES cost (e.g., OneRTX when are costs allocated v. direct?) | EY | 1 | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
Identify potential scope increases through connectivity with OneRTX team
Map examples of incoming costs to mission and service areas in brochure
Support alignment on landing location of cost (cost pool, driver); modeling to be done by OneRTX team not EY
Use identified examples and basis for guidance and go-forward process for incoming ES cost
| Design improved scope approval process | RTX | 2
Understand current scope approval process and shortcomings
Develop recommendations for improvements to process (e.g., workflow, timing, etc.)
Execute improvements to process
Enhance ES Budget governance | [5 empty] | Open
| Assess functional ES budget ownership (e.g., HRIS costs - EAS or HR?) | EY | 2 |  |  | Open
Document budget owners for each cost pool within ES scope (brochure and non-brochure)
Establish guiding principles (e.g., functional apps budgets should sit within function itself)
Assess budget ownership and make recommendations where applicable
"Re-org" cost centers
| Assess BU v. ES budget ownership | EY | 2 |  |  | Open
Define budget types and work with key stakeholders to understand current ownership
Develop clear guidelines that define ownership for each budget category, including roles and responsibilities for budget management, approval processes, and reporting requirements
Develop change & training plan to support future process (including Allocations playbook)
| Review current RTX policy materials and update according to final allocation design (e.g., driver definitions, etc.) | RTX | 2 |  |  | Open
| Consolidate process documentation into Horizon portal and address gaps | EY | 2 |  |  | Open
| Perform change impact assessment | EY | 2
Define change initiatives being addressed and engage key stakeholders
Document current processes as a baseline for change impacts
Evaluate potential impacts of the change
Identify potential risks associated with the change initiatives and develop mitigation plan
Socialize change impacts and risk mitigation plans with stakeholders
| Develop and roll out training materials and plan | RTX | 3 |  |  | Open
Enhance and update Horizon Dashboard
Develop additional views in Horizon
Document detailed requirements (e.g., executive view, total dollar v. variance, etc.)
Identify target areas in dashboard for update and upgrade
Evaluate potential enhancement options
Perform update and improvements to Horizon dashboard
Communicate updates made and host informational sessions on changes / new abilities of dashboard
Socialize changes with RTX and USG (Government Accounting)
USG socialization plan
Develop time phased plan to socialize changes to USG
Provide regular updates to DCMA/DCAA related to upcoming changes and timeline
Provide formal notification of cost accounting practices no later than 10/31/25
Develop and execute training and communcations
Communicate changes to impacted employees and BU’s
Update policies, procedures, and charging guidance based on new drivers
Data / Tech | [5 empty] | Status
Document current and future state data flows | [5 empty] | Open
| Identify driver data sources and level of detail | EY |  | 2025-03-10 | 2025-04-11 | Open | bar: 2025-03-10 to 2025-04-07
Compile a list of data sources that provide information related to drivers
Assess data availability and accessibility at level of detailed required
Develop policies that outline how driver data should be collected, maintained, and reported and specify ownership
Outline and implement processes to regularly monitor compliance with governance policies and data quality standards for driver data sources
| Understand systems landscape and data flows for non-direct ES costs | EY |  | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
Map the current state non-direct charge data flow, illustrating how data is collected, processed and reported
Identify stakeholders involved in non-direct charge data flow
Establish roles for setting policies, reviewing processes, and ensuring adherence to governance standards
Develop policies that outline how non-direct charge data should be collected, processed, stored, and reported and socialize with stakeholders
| Understand systems landscape and data flows for direct ES costs | RTX |  | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
Map the current state direct charge data flow, illustrating how data is collected, processed and reported
Identify stakeholders involved in direct charge data flow
Establish roles for setting policies, reviewing processes, and ensuring adherence to governance standards
Develop policies that outline how direct charge data should be collected, processed, stored, and reported and socialize with stakeholders
| Evaluate opportunities to harness data to optimize ES operational reporting | RTX |  | 2025-07-21 | 2025-10-03 | Open | bar: 2025-07-21 to 2025-09-29
Work with stakeholders to establish KPIs and frequency of reporting
Initiate Horizon improvements aligned to BU feedback (e.g., )
Draft documentation and create reporting templates
Socialize reports with key stakeholders and establish periodic reviews
Leverage technology to enable cost allocations process | [5 empty] | Open
| Explore immediate automation opportunities | EY |  | 2025-09-15 | 2025-10-10 | Open | bar: 2025-09-15 to 2025-10-06
Review existing process to determine which activities may benefit from automation
Evaluate potential automation solutions and compatibility with existing systems
Prioritize technology advancements
Establish high level implementation considerations
| Define requirements for future cost allocations process | EY
Review existing technology processes and assess potential technology capabilities and implementations
Determine requirements needed for technology upgrade
Create detailed plan of requirements and procedures for selecting / implementing EPM, ERP, etc.
| Perform tool selection across various allocation technology options (e.g., EPM, ERP, point solution) | RTX |  | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Centralize allocations data including budgets and base data (potential interim solution in tandem to tool decision/implementation)
Perform system gap analysis across platforms
Identify interim solution pre/post s/4
| Implement improved allocation technology and any identified interim solution | EY |  | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Define clear objectives for the technology implementation
Create a detailed implementation plan that outlines timelines, milestones, and resource requirements
Configure and customize the technology
Develop training materials and conduct training
Perform Cost Impact Model Analysis | [5 empty] | Open
| Direct charge pressure test | EY |  | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
Obtain indirect rate models (i.e., incurred cost submissions) and CAS disclosure statements from all segments, CHO’s, and IHO’s
Obtain contract back log/forecast data by cost element
Assess impact to contracts based on contract type.
Assess administrative burden of capturing new drivers
Refine list of new allocation bases/drivers based on financial impacts and data availability; develop time phased plan to implement changes, as needed.
| Driver pressure test | EY |  | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
Obtain indirect rate models (i.e., incurred cost submissions) and CAS disclosure statements from all segments, CHO’s, and IHO’s
Obtain contract back log/forecast data by cost element
Assess impact to contracts based on contract type.
Assess administrative burden of capturing new drivers
Refine list of new allocation bases/drivers based on financial impacts and data availability; develop time phased plan to implement changes, as needed.
| Detailed cost impact model and analysis | EY |  | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
Based on the list of impacted segments, identify universe of CAS covered contracts
Assess cost impact for each cost accounting practice change
t | Milestone
 | time axis 2025-02-03 to 2025-12-29
Adds - CM
Establish flexible allocations process that incorporates increased future ES scope
Document current scope approval process and design improved process - governance
Create allocations playbook that includes updated process flows, handoffs and criteria for future allocations to accommodate ES growth - governance
Develop comprehensive SOPs and training materials for any updated processes (e.g., direct charge) - governance
Expand scope of assessment to include corporate costs (consistency check)- cost structure / target state design
Host review workshops on final allocation architecture with key finance stakeholders (FPA, Controllership, ES, Gov Acct) - cost structure / target state design
Backlog re-prioritization; define practical next steps on implementation/sprint plan; support near term improvements - add regular milestones for thisevery 8 weeks
Engage key subject matter resources to gather data on allocations requirements, validate findings, verify assumptions, and test hypotheses on streamlining allocations - cost structure / target state design
Identify unique considerations / impacts on allocations (e.g., tax) - cost structure / target state design
Test drivers based on statistical relationships (actuals v. forecast) - cost structure / target state design
Adds - CM
Document upstream and downstream data flow - data and systems mapping
Identify rules / existing logic and opportunities to streamline (reduce rules) - base data maintenance and preparation
Initiate Horizon improvements aligned to BU feedback (e.g., ) - data / reporting
Note on B54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let’s specify the activities we will be taking on here like we do below. As part of this, we will be developing all leadership materials, including Neil-ready quantitative summaries from detailed cost impacts, regular status updates (including risks/mitigations), etc. This program has a lot of eyes, so the TMO-related activity around executive updates for various forums (e.g., Finance Council, Neil reviews) here is not light.
Note on B59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It might be helpful as we continue to build out the details to add in Milestones or deliverables where it makes sense, likely at the title activity level (Direct charge process design). For example, Develop comprehensive SOPs for direct charge would be an action and a deliverable
Note on B120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are we exploring opportunities to assess who should own what? E.g., HRIS is owned by Apps currently but could be evaluated are being owned by HR function in future state
Note on B125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On the roadmap, let’s have a dotted line between this chevron and the direct and non direct process chevrons… for example, the direct decision matrix (activity under design direct process) is a component of / will be cited in this more comprehensive ‘guidance’ for incoming cost
Note on B134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are we exploring opportunities to assess who should own what? E.g., HRIS is owned by Apps currently but could be evaluated are being owned by HR function in future state
Note on B204: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will look very different based on decisions made for which technology will be leveraged; on the roadmap this activity should visually show that (perhaps a dotted line around the chevron)
Note on B234: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have all of these below been addressed and added into the above activities? If yes, lets remove

## Activity Plan
R2R Training Academy - Operating Model
Activities | [7 empty] | Artifacts |  |  | August |  |  |  | September |  |  |  |  | August
1 | Artefact Discovery | Identify existing R2R documentation, policies, SOPs, reports | Owner | Type | Start | End | Status | % of completion | % of review done | % of finalization | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27
1a | Conduct a comprehensive inventory of existing R2R documentation |  | Baldev / Parth | Task | 2025-08-04 | 2025-08-08 | Completed | 50% | 0% | 0% | bar: 2025-08-04
1a.i | Global Process Owner (GPO) Structure |  | Baldev / Parth | Summary Task | 2025-08-04 | 2025-08-14 | In Progress | 56.67% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | R2R process ownership model (centralized, hybrid, federated) | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open | 20% | 0 | 0 | bar: 2025-08-04 to 2025-08-11
|  | RACI matrix for policy, process, and tools | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 100% | 0 | 0 | bar: 2025-08-04 to 2025-08-11
|  | Governance cadence | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open | 50% | 0 | 0 | bar: 2025-08-04 to 2025-08-11
1a.ii | CoE Structure and Scope |  | Baldev / Parth | Summary Task | 2025-08-04 | 2025-08-14 | In Progress | 75% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Innovation governance & advisory | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open | 0 | 0 | 0 | bar: 2025-08-04 to 2025-08-11
|  | Shared services model | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Completed | 100% | 0 | 0 | bar: 2025-08-04 to 2025-08-11
|  | Standardization mandates | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Completed | 100% | 0 | 0 | bar: 2025-08-04 to 2025-08-11
|  | KPIs for GBS / CoE performance | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Completed | 100% | 0 | 0 | bar: 2025-08-04 to 2025-08-11
1a.iii | Skill Assessment Framework |  | Baldev / Parth | Summary Task | 2025-08-04 | 2025-08-14 | In Progress | 63.33% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Role-based learning paths | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Tool 1 - BlackLine | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Completed | 100% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Tool 2 - Trintech | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Completed | 100% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Tool 3 - ARCS | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Completed | 100% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Tool 4 - Agentic AI | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | R2R personas | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 80% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
1a.iv | Change Impact Assessment |  | Baldev / Parth | Summary Task | 2025-08-04 | 2025-08-14 | In Progress | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Communication plans | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Stakeholder mapping | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Adoption KPIs | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
1a.v | Maturity Model |  | Baldev / Parth | Summary Task | 2025-08-04 | 2025-08-14 | In Progress | 80% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Self-assessment toolkit | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 60% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Roadmap builder with custom recommendations | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open | 100% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
1a.vi | Client Credentials |  | Baldev / Parth | Summary Task | 2025-08-04 | 2025-08-14 | In Progress | 75% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | List of R2R projects handled by GDS team | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 50% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Team skillset on R2R project delivery | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Open |  | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Client case studies on R2R projects | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | Completed | 100% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
1.a.vii | Operating Model Structure and Chevrons |  | Baldev / Parth | Summary Task | 2025-08-04 | 2025-08-14 | In Progress | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Operating model encompassing both upstream & downstream activities | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
|  | Org design aligned with leading practices for R2R operating model | Baldev / Parth | Task | 2025-08-04 | 2025-08-14 | In Progress | 0% | 0% | 0% | bar: 2025-08-04 to 2025-08-11
1b | Analysis to identify gaps in the current documentation |  | Baldev / Parth | Task | 2025-08-11 | 2025-08-14 | Completed | bar: 2025-08-11
1c | Engage other towers' stakeholders to gather additional documentation |  | Baldev / Parth | Task | 2025-08-18 | 2025-08-22 | In Progress | bar: 2025-08-18
2 | Create New Artefacts | As per the Operating Model & Capability Enablement tower list | Owner | Type | Start | End | Status |  |  |  | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27
2a.i | Develop new artefacts from the ground up, following the Op Model tower list - Wave 1 |  | Baldev / Parth | Summary Task | 2025-08-18 | 2025-08-22 | In Progress | bar: 2025-08-18
|  | R2R personas | Baldev / Parth | Task | 2025-08-18 | 2025-08-22 | In Progress | bar: 2025-08-18
|  | KPIs for GBS / CoE performance | Baldev / Parth | Task | 2025-08-18 | 2025-08-22 | In Progress | bar: 2025-08-18
|  | Self-assessment toolkit | Baldev / Parth | Task | 2025-08-18 | 2025-08-22 | In Progress | bar: 2025-08-18
2a.ii | Develop new artefacts from the ground up, following the Op Model tower list - Wave 2 |  | Baldev / Parth | Summary Task | 2025-08-25 | 2025-08-29 | Open | bar: 2025-08-25
|  | Operating Model structure | Baldev / Parth | Task | 2025-08-25 | 2025-08-29 | Open | bar: 2025-08-25
|  | R2R process ownership model (centralized, hybrid, federated) | Baldev / Parth | Task | 2025-08-25 | 2025-08-29 | Open | bar: 2025-08-25
|  | Team skillset on R2R project delivery | Baldev / Parth | Task | 2025-08-25 | 2025-08-29 | Open | bar: 2025-08-25
|  | Communication plans and Stakeholder mapping | Baldev / Parth | Task | 2025-08-25 | 2025-08-29 | Open | bar: 2025-08-25
|  | Others | Baldev / Parth | Task | 2025-08-25 | 2025-08-29 | Open | bar: 2025-08-25
2b | Collaborate with stakeholders from other towers to draft these new artefacts |  | Baldev / Parth | Task | 2025-08-18 | 2025-08-29 | In Progress | bar: 2025-08-18 to 2025-08-25
2c | Organize artefacts in a logical structure for easy access |  | Baldev / Parth | Task | 2025-08-25 | 2025-08-29 | Open | bar: 2025-08-25
2d | Tailor existing artefacts to incorporate the R2R perspective within the broader finance process |  | Baldev / Parth | Task | 2025-08-18 | 2025-09-05 | Open | bar: 2025-08-18 to 2025-09-01
3 | Artefact Review | Assess completeness and accuracy of artefacts | Owner | Type | Start | End | Status |  |  |  | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27
3a | Evaluate the completeness and accuracy of all artefacts prior to submission for validation |  | Baldev | Task | 2025-09-08 | 2025-09-09 | Open | bar: 2025-09-08
3b | Submit the draft of the artefacts for content review |  | Baldev | Deliverable | 2025-09-09 | 2025-09-09 | Open | bar: 2025-09-08
3c | Solicit feedback from Ram |  | Ram | Task | 2025-09-08 | 2025-09-12 | Open | bar: 2025-09-08
3d | Integrate necessary revisions as per the feedback |  | Baldev / Parth | Task | 2025-09-08 | 2025-09-19 | Open | bar: 2025-09-08 to 2025-09-15
4 | Artefact Preparation | Clean, format, standardize key data sets | Owner | Type | Start | End | Status |  |  |  | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27
4a | Ensure consistent formatting across all artefacts |  | Baldev / Parth | Task | 2025-09-01 | 2025-09-19 | Open | bar: 2025-09-01 to 2025-09-15
4b | Cleanse and validate key data sets to guarantee their accuracy |  | Baldev / Parth | Task | 2025-09-01 | 2025-09-19 | Open | bar: 2025-09-01 to 2025-09-15
4c | Organize artefacts in a logical structure for easy access |  | Baldev / Parth | Task | 2025-09-01 | 2025-09-19 | Open | bar: 2025-09-01 to 2025-09-15
4d | Submit the polished and formatted version of the artefacts for final validation |  | Baldev | Deliverable | 2025-09-19 | 2025-09-19 | Open | bar: 2025-09-15
5 | Artefact Validation | Review artefacts and data with project leads | Owner | Type | Start | End | Status |  |  |  | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27
5a | Schedule review sessions with Shruti, Prabhu, and Ram |  | Baldev / Parth | Task | 2025-09-22 | 2025-09-26 | Open | bar: 2025-09-22
5b | Collect feedback on artefacts and data sets |  | Baldev / Parth | Task | 2025-09-22 | 2025-09-26 | Open | bar: 2025-09-22
5c | Document validation outcomes |  | Ram | Task | 2025-09-22 | 2025-09-26 | Open | bar: 2025-09-22
5d | Submit the final document after making any necessary changes based on the validation outcomes |  | Baldev | Deliverable | 2025-09-29 | 2025-10-01 | Open | bar: 2025-09-29
6 | Artefact Finalization | Version control, document storage for tool use | Owner | Type | Start | End | Status |  |  |  | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27
6a | Store finalized documents in a centralized repository |  | Ram | Task | 2025-09-29 | 2025-10-01 | Open | bar: 2025-09-29
6b | Implement version control systems for all artefacts |  | Ram | Task | 2025-09-29 | 2025-10-01 | Open | bar: 2025-09-29
6c | Create a user guide for accessing and using artefacts |  | Ram | Task | 2025-09-29 | 2025-10-01 | Open | bar: 2025-09-29
[11 empty] | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27

## Data Request
Operating Model | Item | Item Description / Data Requested | Open Questions | Ram / Shruti / Prabhu Response
Organization Structure / Operating Model / GPOs | R2R process ownership model (centralized, hybrid, federated) | R2R Org Structure - encompassing GBS, COEs, GPOs, and Controllers, representing centralized, hybrid, and federated models |  |  | Parth
| Interaction Model / Process Maps | Upstream and Downstream interactions with the R2R process, involving functions such as OTC, PTP, FP&A, Tax, and Treasury
| Governance cadence |  | Our understanding is that this illustrates the governance framework for the entire R2R cycle, including weekly, monthly and annual closing processes, along with the stakeholders involved | Cadence lead by the GPO to look at different aspects of the GBS/CoE performance for R2R: 1) Policy adherence, 2) KPIs, 3) continuous improvement, 4) tool and process closer to Best-in-class, 5) status of improvement opportunities, etc. Responsibilities of each function in the GPO, cross-functional interaction with other finance processes | Baldev
COE Structure / Scope | Innovation governance and advisory |  | Are we aiming to establish a COE structure and highlight its interaction with the R2R organization, or should we present a list of activities that can be performed by the R2R team? | CoE: Set of activities on which, 1) new tools are utilized, 2) best-in-class methodology is deployed, 3) innovation practices. CoE is optional Brainstorming of each opportunity identified and cost-benefit analysis Layers of Innovation - identified, triggered, designed, build, implemented | Later
Change Impact Assessment | Any material relevant to Change Impact Assessment | Relevant documentation such as communication plans, stakeholder mapping, etc. to evaluate the effects of changes on the R2R organization |  | Change -> Review -> Approval (Change control mechanism) Matrix that shows the assessment of the Change Summary of the assessment with the impact of Change on different parties | Parth
Maturity Models | Roadmap builder with custom recommendations |  | Could you please provide more details on what we intend to convey in this context? | Roadmap showcasing how to move from one maturity model step to the next one Criticality, cross-dependencies, technology/process improvement Framework of prioritization - Quick wins, Interim, Long-term | Baldev / Parth
| Self-assessment toolkit | Toolkit designed to help individuals evaluate their current capabilities and identify areas for improvement | Can you please provide more details on what exactly are we looking for in here? We have visibility into maturity model for R2R and sub-processes (intercompany, revenue recognition, etc.) across the operating model levers (people, technology, organization, etc.). Do they meet the requirement here? | Focus on People aspect - Skill gap assessment Focus on Tool aspect - Like the survey EY Pulse roll out Based on the current KPIs - Identify the current STAGE of the maturity model | Parth
Client Credentials | Team skillset on R2R project delivery | Key competencies and expertise of the team involved in delivering R2R projects |  |  | Baldev
Skill Assessment Framework | Role-based learning paths | Customized training programs tailored to specific roles, aimed at enhancing skills and knowledge relevant to those positions | Could you please provide more details on what we intend to convey in this context?
| Tool 4 - Alteryx | Data/content to be requested from Tower 4 (Master Data and Analytics Layer) | Do we need these tools for R2R processes? We have relevant materials for R2R tools such as BlackLine, Arcs, FCCS, Trintech, etc. | How does Agentic helps out in the R2R process and tools? Don't focus on these ancillary tools | Baldev / Parth
| Tool 5 - PowerBI | Data/content to be requested from Tower 4 (Master Data and Analytics Layer)
| Tool 6 - UiPath | Data/content to be requested from Tower 3 (Digital Enablers & Automation Layer)
| Tool 7 - Excel AI | Data/content to be requested from Tower 3 (Digital Enablers & Automation Layer)

## Project Plan_vRoadmap_OLD (hidden)
Raytheon (RTX) Cost Allocations Transformation - Phase 2
Activities | [7 empty] | Month 0 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
[8 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44
 | time axis 2025-02-03 to 2025-12-29
0. Engagement Administration and Economics |  | Owner |  | Wave | Start | End | Status
1 | Setup engagement in GEAR (incl. upload of SOW and MSA) | EY |  |  |  |  | Open
2 | Create SQ plan | EY |  |  |  |  | Open
3 | Review RTX Data Privacy requirements | EY |  |  |  |  | Open
4 | Update engagement win status | EY |  |  |  |  | Open
5 | Perform ETC #1 | EY |  |  |  |  | Open
6 | Execute internal kickoff | EY |  |  |  |  | Open
7 | Distribute invoice #1 | EY |  |  |  |  | Open
8 | Perform ETC #2 | EY |  |  |  |  | Open
9 | Perform ETC #3 | EY |  |  |  |  | Open
10 | Perform ETC #4 (if needed) | EY |  |  |  |  | Open
11 | Distribute invoice #2 | EY |  |  |  |  | Open
Phase 1 Extension |  | Owner | Type | Wave | Start | End | Status
Define new driver data |  |  |  | 0 |  |  | Open
| Create and Facilitate completion of template for new drivers to service owners | EY | Summary Task | 0 | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Create data collection template for all proposed drivers (e.g., calculations, level of detail, sources, owners, frequency) and share with service owners | EY | Task | 0 | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Create base data catalog - including new data collected, forecast and actuals | EY | Task | 0 | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Perform high level analysis of forecast to actuals to confirm predictability hypotheses | EY | Task | 0 | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
Finalize and socialize Direct Charge decision Matrix |  |  |  | 0 |  |  | Open
| Create Direct Charge decision matrix | EY | Summary Task |  | 2025-02-10 | 2025-02-21 | bar: 2025-02-10 to 2025-02-17
| Finalize Direct Charge decision matrix | EY | Task |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Evaluate direct charge cost pools with ES Finance (2nd round) | EY | Task |  | 2025-02-10 | 2025-02-21 | bar: 2025-02-10 to 2025-02-17
| Evaluate direct charge cost pools with OneRTX and Service Catalog teams | EY | Task |  | 2025-02-10 | 2025-02-21 | bar: 2025-02-10 to 2025-02-17
Support Socialization of Allocation Architecture | [6 empty] | Open
| Facilitate detailed reviews with stakeholders | EY | Summary Task |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Evaluate drivers with ES Finance (2nd Round) | EY / RTX | Task |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Evaluate drivers and cost pools with Government accounting team | EY / RTX | Task |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Evaluate drivers with ES Services owners | EY / RTX | Task |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Engage OneRTX team and Service Catalog team on cost categories in order to future proof drivers and pools | EY / RTX | Task |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Develop agenda and materials for BU outreach - cost pools, drivers, direct charge | EY | Task |  | 2025-02-24 | 2025-02-28 | bar: 2025-02-24
Refine model, perform scenarios | [6 empty] | Open
| Refine high level cost impact model with new driver data | EY | Summary Task |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Iterate model to reflect new driver data | EY | Task |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Iterate model to reflect additional pressure tested scenarios | EY | Task |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Iterate model to reflect direct charge scenarios (omission of costs) | EY | Task |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Socialize high level impacts | EY | Task |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
TMO |  | Owner | Type | Wave | Start | End | Status
Engagement Management |  | EY |  |  | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Transformation Management |  | EY |  |  | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
| Monitor Program | EY | Summary Task
Monitor project progress (e.g. schedule, dependencies, quality, etc)
Update program management tools updated to drive program transparency (e.g. RAIDD log, project plan)
Conduct program status reporting on a regular basis
| Prepare External Status Updates | EY | Summary Task
| Develop external status template, including risks and mitigations | EY | Task |  | 2025-03-03 | 2025-03-07
| Schedule all status review meetings | EY | Task |  | 2025-03-03 | 2025-03-05
| Prepare and distribute Status Update #1 | EY | Deliverable |  | 2025-03-03 | 2025-03-07
| Prepare and distribute Status Update #2 | EY | Deliverable |  | 2025-03-10 | 2025-03-14
| Prepare and distribute Status Update #3 | EY | Deliverable |  | 2025-03-17 | 2025-03-21
| Prepare and distribute Status Update #4 | EY | Deliverable |  | 2025-03-24 | 2025-03-28
| Prepare and distribute Status Update #5 | EY | Deliverable |  | 2025-03-31 | 2025-04-04
| Prepare and distribute Status Update #6 | EY | Deliverable |  | 2025-04-07 | 2025-04-11
| Prepare and distribute Status Update #7 | EY | Deliverable |  | 2025-04-14 | 2025-04-18
| Prepare and distribute Status Update #8 | EY | Deliverable |  | 2025-04-21 | 2025-04-25
| Prepare and distribute Status Update #9 | EY | Deliverable |  | 2025-04-28 | 2025-05-02
| Prepare and distribute Status Update #10 | EY | Deliverable |  | 2025-05-05 | 2025-05-09
| Prepare and distribute Status Update #11 | EY | Deliverable |  | 2025-05-12 | 2025-06-16
| Prepare and distribute Status Update #12 | EY | Deliverable |  | 2025-05-19 | 2025-05-23
| Host Steering Committee | EY | Summary Task
| Prepare materials for SteerCo #3: Cost Impact Analysis | EY | Task |  | 2025-04-07 | 2025-05-09
| Schedule SteerCo #3 | EY | Task |  |  | 2025-03-14
| Review SteerCo #3 materials with Gerardo | EY | Task |  | 2025-05-12 | 2025-05-16
| Finalize and distribute SteerCo #3 materials | EY | Deliverable |  |  | 2025-05-16
| Host SteerCo #3 | EY | Task |  | 2025-05-19 | 2025-05-23
| Prepare for Finance Council | EY | Summary Task
| Prepare materials for March Finance Council | EY | Task
| Participate in March Finance Council | EY | Task
| Prepare materials for April Finance Council | EY | Task
| Participate in April Finance Council | EY | Task
| Prepare materials for May Finance Council | EY | Task
| Participate in May Finance Council | EY | Task
| Additional Leadership Updates | EY | Summary Task
Core Process |  | Owner | Type | Wave | Start | End | Status
Standardize and Streamline ES Cost Allocation Process |  | EY |  |  | 2025-03-03 | 2025-10-28 | Open | bar: 2025-03-03 to 2025-10-27
| Direct charge process definition & design | EY | Summary Task | 1 | 2025-03-03 | 2025-04-18 | Open | bar: 2025-03-03 to 2025-04-14
| Map and define the current state direct charge allocation process (SIPOC) with service-based cost pool structure | EY | Task | 1 | 2025-03-03 | 2025-03-17 | bar: 2025-03-03 to 2025-03-17
| SIPOC diagram with service-based cost pool structure | EY | Deliverable | 1 | 2025-03-17 | 2025-03-17 | bar: 2025-03-17
| Define direct charge criteria | EY | Task | 1 | 2025-03-03 | 2025-03-10 | bar: 2025-03-03 to 2025-03-10
| Direct charge criteria document | EY | Deliverable | 1 | 2025-03-10 | 2025-03-10 | bar: 2025-03-10
| Create direct charge process flows and procedures | EY | Task | 1 | 2025-03-17 | 2025-03-31 | bar: 2025-03-17 to 2025-03-31
| Direct charge process flow and procedures | EY | Deliverable | 1 | 2025-03-31 | 2025-03-31 | bar: 2025-03-31
| Develop comprehensive SOPs and training materials for updated processes | RTX | Task | 1 | 2025-04-01 | 2025-04-18 | bar: 2025-04-07 to 2025-04-14
| Direct charge SOPs & training materials | RTX | Deliverable | 1 | 2025-04-14 | 2025-04-14 | bar: 2025-04-14
| Non-direct process definition & design | EY | Summary Task | 1 | 2025-04-21 | 2025-06-02 | Open | bar: 2025-04-21 to 2025-06-02
| Map and define the current state non-direct allocation process (SIPOC) with service-based cost pool structure | EY | Task | 1 | 2025-04-21 | 2025-05-05 | bar: 2025-04-21 to 2025-05-05
| SIPOC diagram with service-based cost pool structure | EY | Deliverable | 1 | 2025-05-05 | 2025-05-05 | bar: 2025-05-05
| Outline opportunities for standardization and streamlining within process | EY | Task | 1 | 2025-04-21 | 2025-05-05 | bar: 2025-04-21 to 2025-05-05
| Test opportunity hypotheses for all non-direct allocations | EY | Task | 1 | 2025-04-28 | 2025-05-26 | bar: 2025-04-28 to 2025-05-26
| Non-direct opportunity hypotheses summary | EY | Deliverable | 1 | 2025-05-12 | 2025-05-12 | bar: 2025-05-12
| Design streamlined process incorporating upstream data collection and downstream reporting | EY | Task | 1 | 2025-05-05 | 2025-05-26 | bar: 2025-05-05 to 2025-05-26
| Non-direct streamlined process design mapping | EY | Deliverable | 1 | 2025-05-26 | 2025-05-26 | bar: 2025-05-26
| Refine allocation architecture to incorpoate Future ES scope | EY | Task | 1 | 2025-05-05 | 2025-05-26 | bar: 2025-05-05 to 2025-05-26
| Develop comprehensive SOPs and training materials for updated processes | EY | Task | 1 | 2025-05-26 | 2025-06-02 | bar: 2025-05-26 to 2025-06-02
| Non-direct SOPs & training materials | RTX | Deliverable | 1 | 2025-06-02 | 2025-06-02 | bar: 2025-06-02
| Model and Implement non-direct charge changes to Brochure | RTX/EY | Task | 1 | 2025-05-26 | 2025-06-02 | bar: 2025-05-26 to 2025-06-02
| Brochure updates summary (non-direct charge changes) | RTX/EY | Deliverable | 1 | 2025-06-02 | 2025-06-02 | bar: 2025-06-02
| Host review workshops on final allocation architecture with key finance stakeholders (FPA, Controllership, ES, Gov Acct) | RTX/EY | Task | 1 | 2025-05-26 | 2025-06-02 | bar: 2025-05-26 to 2025-06-02
| Streamline upstream/downstream timely distribution to BUs for Non-Direct Process | RTX | Summary Task | 3 | 2025-09-01 | 2025-10-28 | Open | bar: 2025-09-01 to 2025-10-27
| Identify current process for distribution and submission of brochure | RTX | Task | 3 | 2025-09-01 | 2025-09-15 | bar: 2025-09-01 to 2025-09-15
| Determine pain points and opportunities with adjustment of brochure distribution | RTX | Task | 3 | 2025-09-15 | 2025-09-29 | bar: 2025-09-15 to 2025-09-29
| Standardize communication procedures for receiving and submitting of brochure | RTX | Task | 3 | 2025-09-29 | 2025-10-13 | bar: 2025-09-29 to 2025-10-13
| Socialize standardized process for distribution of brochure to BUs | RTX | Task | 3 | 2025-10-13 | 2025-10-28 | bar: 2025-10-13 to 2025-10-27
| Re-align on Benchmark cost structure against industry standards and best practices | RTX | Task | 3 | 2025-10-20 | 2025-10-28 | bar: 2025-10-20 to 2025-10-27
Execute changes in the system to consolidate and eliminate cost centers |  | EY |  |  | 2025-05-02 | 2025-07-15 | Open | bar: 2025-05-05 to 2025-07-14
| Align Cost Centers to Service Catalog | EY | Summary Task | 2 | 2025-05-12 | 2025-06-09 | Open | bar: 2025-05-12 to 2025-06-09
| Identify comprehensive list of services offered by ES and identify discrepancies in Brochure | EY | Task | 2 | 2025-05-12 | 2025-05-19 | bar: 2025-05-12 to 2025-05-19
| Identify opportunities to streamline cost centers in Brochure (i.e., 3 cost centers per Service) | EY | Task | 2 | 2025-05-19 | 2025-06-02 | bar: 2025-05-19 to 2025-06-02
| Update cost centers in ES Brochure to map to Service Catalog | EY | Task | 2 | 2025-06-02 | 2025-06-09 | bar: 2025-06-02 to 2025-06-09
| Evaluate consolidation & assess corporate cost inclusion | RTX | Summary Task | 2 | 2025-05-02 | 2025-07-15 | Open | bar: 2025-05-05 to 2025-07-14
| Conduct a comprehensive review of the current cost center structure and identify areas of consolidation | RTX | Task | 2 | 2025-05-02 | 2025-06-02 | bar: 2025-05-05 to 2025-06-02
| Expand scope of assessment to include corporate costs (consistency check) | RTX | Task | 2 | 2025-06-02 | 2025-07-15 | bar: 2025-06-02 to 2025-07-14
| Future proof cost centers for ES growth | RTX | Summary Task | 2 | 2025-06-23 | 2025-07-15 | Open
| Develop standardized guidelines for cost centers, including guidelines for future ES costs, maintenance, etc. | RTX | Task | 2 | 2025-06-23 | 2025-06-20 | Open
| Socialize new structure with ES stakeholders and outlines roles / responsibilities for maintaing cost centers | RTX | Task | 2 | 2025-06-23 | 2025-07-07 | bar: 2025-06-23 to 2025-07-07
| Establish and implement periodic reviews of guidelines and cost centers | RTX | Task | 2 | 2025-07-07 | 2025-07-15 | bar: 2025-07-07 to 2025-07-14
Streamline layers of cost allocation from ES to receiving cost centers |  | EY |  |  | 2025-06-16 | 2025-10-10 | Open | bar: 2025-06-16 to 2025-10-06
| Identify receiving cost centers and align drivers | EY | Summary Task | 2 | 2025-06-16 | 2025-07-21 | Open | bar: 2025-06-16 to 2025-07-21
| Evaluate driver data to lowest BU cost mapping level | EY | Task | 2 | 2025-06-16 | 2025-06-30 | bar: 2025-06-16 to 2025-06-30
| Evaluate direct charge impact on BUs cost mapping | EY | Task | 2 | 2025-06-16 | 2025-06-30 | bar: 2025-06-16 to 2025-06-30
| Review draft cost mapping with ES Finance Leads & BU Leads | EY | Task | 2 | 2025-06-30 | 2025-07-06 | bar: 2025-06-30
| Review draft cost mapping with BU leads | EY | Task | 2 | 2025-07-14 | 2025-07-20 | bar: 2025-07-14
| Socialize refined driver data to BUs & ES Leads | EY | Task | 2 | 2025-07-15 | 2025-07-21 | bar: 2025-07-21
| Document opportunities to remove layers of cost allocation within CA and PW | EY | Summary Task | 3 | 2025-07-21 | 2025-10-10 | Open | bar: 2025-07-21 to 2025-10-06
| Workshop new structure with ES functional leads and gather feedback | EY | Task | 3 | 2025-07-21 | 2025-09-01 | bar: 2025-07-21 to 2025-09-01
| Workshop new structure with BU leads and gather feedback | EY | Task | 3 | 2025-08-01 | 2025-09-01 | bar: 2025-08-04 to 2025-09-01
| Incorporate feedback from current process and develop future state process | EY | Task | 3 | 2025-09-01 | 2025-09-15 | bar: 2025-09-01 to 2025-09-15
| Socialize standardized process for distribution of brochure to BUs | RTX | Task | 3 | 2025-09-15 | 2025-09-30 | bar: 2025-09-15 to 2025-09-29
| Implement changes for brochure release | RTX | Task | 3 | 2025-09-15 | 2025-10-10 | bar: 2025-09-15 to 2025-10-06
Document current and future state data flows |  | RTX/EY |  |  | 2025-03-03 | 2025-10-03 | Open | bar: 2025-03-03 to 2025-09-29
| Identify driver data sources and level of detail | EY | Summary Task | 1 | 2025-03-10 | 2025-04-11 | Open | bar: 2025-03-10 to 2025-04-07
| Engage key subject matter resources to gather data on allocations requirements | EY | Task | 1 | 2025-03-10 | 2025-03-16 | bar: 2025-03-10
| Compile a list of data sources that provide information related to drivers | EY | Task | 1 | 2025-03-10 | 2025-03-20 | bar: 2025-03-10 to 2025-03-17
| Assess data availability and accessibility at level of detailed required | EY | Task | 1 | 2025-03-10 | 2025-03-20 | bar: 2025-03-10 to 2025-03-17
| Review the collected cost data to identify inconsistencies or discrepancies in how costs are allocated across different services | EY | Task | 1 | 2025-03-16 | 2025-03-24 | bar: 2025-03-17 to 2025-03-24
| Develop policies that outline how driver data should be collected, maintained, and reported and specify ownership | EY | Task | 1 | 2025-03-24 | 2025-04-07 | bar: 2025-03-24 to 2025-04-07
| Outline and implement processes to regularly monitor compliance with governance policies and data quality standards for driver data sources | EY | Task | 1 | 2025-03-27 | 2025-04-11 | bar: 2025-03-31 to 2025-04-07
| Understand systems landscape and data flows for non-direct ES costs | EY | Summary Task | 1 | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
| Map the current state non-direct charge data flow, illustrating how data is collected, processed and reported | EY | Task | 1 | 2025-03-03 | 2025-03-17 | bar: 2025-03-03 to 2025-03-17
| Identify stakeholders involved in non-direct charge data flow | EY | Task | 1 | 2025-03-17 | 2025-03-24 | bar: 2025-03-17 to 2025-03-24
| Identify system requirements and constraints for future state optimization | EY | Task | 1 | 2025-03-17 | 2025-03-24 | bar: 2025-03-17 to 2025-03-24
| Establish roles for setting policies, reviewing processes, and ensuring adherence to governance standards | EY | Task | 1 | 2025-03-24 | 2025-04-14 | bar: 2025-03-24 to 2025-04-14
| Develop policies that outline how non-direct charge data should be collected, processed, stored, and reported and socialize with stakeholders | EY | Task | 1 | 2025-04-21 | 2025-05-02 | bar: 2025-04-21 to 2025-04-28
| Understand systems landscape and data flows for direct ES costs | RTX | Summary Task | 1 | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
| Map the current state direct charge data flow, illustrating how data is collected, processed and reported | RTX | Task | 1 | 2025-03-03 | 2025-03-17 | bar: 2025-03-03 to 2025-03-17
| Identify stakeholders involved in direct charge data flow | RTX | Task | 1 | 2025-03-17 | 2025-03-24 | bar: 2025-03-17 to 2025-03-24
| Document integration points between direct and non-direct data flows | RTX | Task | 1 | 2025-03-17 | 2025-03-24 | bar: 2025-03-17 to 2025-03-24
| Establish roles for setting policies, reviewing processes, and ensuring adherence to governance standards | RTX | Task | 1 | 2025-03-24 | 2025-04-14 | bar: 2025-03-24 to 2025-04-14
| Develop policies that outline how direct charge data should be collected, processed, stored, and reported and socialize with stakeholders | RTX | Task | 1 | 2025-04-21 | 2025-05-02 | bar: 2025-04-21 to 2025-04-28
| Evaluate opportunities to harness data to optimize ES operational reporting | RTX | Summary Task | 3 | 2025-07-21 | 2025-10-03 | Open | bar: 2025-07-21 to 2025-09-29
| Work with stakeholders to establish KPIs and frequency of reporting | RTX | Task | 3 | 2025-07-21 | 2025-08-30 | bar: 2025-07-21 to 2025-08-25
| Initiate Horizon improvements aligned to BU feedback (e.g., ) | RTX | Task | 3 | 2025-08-15 | 2025-09-15 | bar: 2025-08-18 to 2025-09-15
| Draft documentation and create reporting templates | RTX | Task | 3 | 2025-09-15 | 2025-10-01 | bar: 2025-09-15 to 2025-09-29
| Socialize reports with key stakeholders and establish periodic reviews | RTX | Task | 3 | 2025-09-24 | 2025-10-03 | bar: 2025-09-29
Update CAS Disclosure statements (Government Accounting) |  | EY |  |  | 2025-02-28 | 2025-10-27 | Open | bar: 2025-03-03 to 2025-10-27
| Identify cost accounting changes | EY | Summary Task | 1 | 2025-02-28 | 2025-05-30 | Open | bar: 2025-03-03 to 2025-05-26
| Assess existing ES CAS Disclosure Statements to inventory cost accounting practices changes | EY | Task | 1 | 2025-05-05 | 2025-05-16 | bar: 2025-05-05 to 2025-05-12
| Identify impacted CHO , IHO, and Segment pools receiving allocations from ES. | EY | Task | 1 | 2025-05-05 | 2025-05-16
| Assess existing CHO, IHO, and Segment CAS Disclosure Statements to inventory cost accounting practices changes | EY | Task | 1 | 2025-05-05 | 2025-05-16
| Revise CAS disclosure statements | EY | Summary Task | 2 | 2025-05-05 | 2025-10-27 | Open | bar: 2025-05-05 to 2025-10-27
| Update ES CAS Disclosure Statements based on new allocation bases/drivers | EY | Deliverable | 2 | 2025-05-16 | 2025-06-30 | bar: 2025-05-19 to 2025-06-30
| Update existing CHO, IHO, and Segment CAS Disclosure Statements, as needed, based on updated allocations from ES. | EY | Deliverable |  | 2025-05-16 | 2025-07-31
| Prepare forward pricing and provisional billing rate proposals | EY | Summary Task | 2 | 2025-05-05 | 2025-10-27 | Open | bar: 2025-05-05 to 2025-10-27
| Provide BU’s with updated ES allocation data | EY | Task | 2
| Assist BU’s in the incorporation of updated ES allocations into forward pricing and provisional billing rate proposals, as needed | EY | Task | 2
Perform Cost Impact Model Analysis (Government Accounting) |  | EY |  |  | 2025-03-17 | 2025-08-25 | Open | bar: 2025-03-17 to 2025-08-25
| Direct charge pressure test | EY | Summary Task | 1 | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
| Obtain indirect rate models (i.e., incurred cost submissions) and CAS disclosure statements from all segments, CHO’s, and IHO’s impacted by new direct allocations from ES | EY | Task | 1 | 2025-03-17 | 2025-03-31 | bar: 2025-03-17 to 2025-03-31
| Obtain contract back log/forecast data by cost element | EY | Task | 1 | 2025-03-17 | 2025-03-31 | bar: 2025-03-17 to 2025-03-31
| Assess impact to contracts based on contract type. | EY | Task | 1 | 2025-03-31 | 2025-04-18 | bar: 2025-03-31 to 2025-04-14
| Assess administrative burden of capturing new drivers | EY | Task | 1
| Refine list of new direct charge costs based on financial impacts and data availability; develop time phased plan to implement changes, as needed. | EY | Task | 1 | 2025-04-21 | 2025-05-02 | bar: 2025-04-21 to 2025-04-28
| Driver pressure test | EY | Summary Task | 1 | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
| Obtain contract back log/forecast data by cost element | EY | Task | 1 | 2025-03-17 | 2025-03-31 | bar: 2025-03-17 to 2025-03-31
| Assess impact to contracts based on contract type. | EY | Task | 1 | 2025-03-31 | 2025-04-18 | bar: 2025-03-31 to 2025-04-14
| Assess administrative burden of capturing new drivers | EY | Task | 1 | 2025-03-31 | 2025-04-18 | bar: 2025-03-31 to 2025-04-14
| Refine list of new allocation bases/drivers based on financial impacts and data availability; develop time phased plan to implement changes, as needed. | EY | Task | 1 | 2025-04-21 | 2025-05-02 | bar: 2025-04-21 to 2025-04-28
| GDM & Detailed cost impact model and analysis | EY | Summary Task | 2 | 2025-05-02 | 2025-08-25 | Open | bar: 2025-05-05 to 2025-08-25
| Based on the list of impacted segments, identify universe of CAS covered contracts | EY | Task | 2 | 2025-05-02 | 2025-06-30 | bar: 2025-05-05 to 2025-06-30
| Assess cost impact for each cost accounting practice change | EY | Task | 2 | 2025-05-02 | 2025-08-15 | bar: 2025-05-05 to 2025-08-11
| Deliver results of GDM cost impact to RTX | EY | Deliverable | 2 | 2025-08-18 | 2025-08-25
Business Partnering |  | Owner |  |  | Start | End | Open
Enhance governance around ES budgets |  | RTX/EY |  |  | 2025-03-17 | 2025-05-26 | Open | bar: 2025-03-17 to 2025-05-26
| Document service catalog and cost structure mapping (e.g. cost centers map to which service area) | RTX | Summary Task | 1 | 2025-03-17 | 2025-05-26 | Open | bar: 2025-03-17 to 2025-05-26
| Identify target service areas within each mission area | RTX | Task | 1 | 2025-03-17 | 2025-04-01 | bar: 2025-03-17 to 2025-03-31
| Establish service area mapping of cost pools | EY | Task | 1 | 2025-04-07 | 2025-05-12 | bar: 2025-04-07 to 2025-05-12
| Develop documentation of new structure and mapping of cost pools within service areas | EY | Task | 1 | 2025-05-15 | 2025-05-26 | bar: 2025-05-19 to 2025-05-26
| Defined cost pool consolidation opportunities | EY | Deliverable | 1
| Define guidance and process for incoming ES cost (e.g., OneRTX when are costs allocated v. direct?) | EY | Summary Task | 1 | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
| Identify potential scope increases through connectivity with OneRTX team | EY | Task | 1 | 2025-03-17 | 2025-04-05 | bar: 2025-03-17 to 2025-03-31
| Map examples of incoming costs to mission and service areas in brochure | EY | Task | 1 | 2025-03-30 | 2025-04-14 | bar: 2025-03-31 to 2025-04-14
| Support alignment on landing location of cost (cost pool, driver); modeling to be done by OneRTX team not EY | EY | Task | 1 | 2025-04-01 | 2025-04-21 | bar: 2025-04-07 to 2025-04-21
| Use identified examples and basis for guidance and go-forward process for incoming ES cost | EY | Task | 1 | 2025-04-21 | 2025-05-02 | bar: 2025-04-21 to 2025-04-28
| Design improved scope approval process | RTX | Summary Task | 1 | 2025-04-01 | 2025-05-10 | Open | bar: 2025-04-07 to 2025-05-05
| Understand current scope approval process and shortcomings | RTX | Task | 1 | 2025-04-01 | 2025-04-14 | bar: 2025-04-07 to 2025-04-14
| Develop recommendations for improvements to process (e.g., workflow, timing, etc.) | RTX | Task | 1 | 2025-04-10 | 2025-04-28 | bar: 2025-04-14 to 2025-04-28
| Execute improvements to process | RTX | Task | 1 | 2025-04-28 | 2025-05-10 | bar: 2025-04-28 to 2025-05-05
| Evaluate ES Budget Ownership (e.g., HRIS costs - EAS or HR?) | RTX/EY | Summary Task | 1 | 2025-04-01 | 2025-05-26 | Open | bar: 2025-04-07 to 2025-05-26
| Document budget owners for each cost pool within ES scope (brochure and non-brochure) | RTX | Task | 1 | 2025-04-01 | 2025-04-14 | Open | bar: 2025-04-07 to 2025-04-14
| Establish guiding principles (e.g., functional apps budgets should sit within function itself) | EY | Task | 1 | 2025-04-14 | 2025-05-11 | bar: 2025-04-14 to 2025-05-05
| Assess budget ownership and make recommendations where applicable | EY | Task | 1 | 2025-05-12 | 2025-05-26 | bar: 2025-05-12 to 2025-05-26
| ES Governance Playbook | RTX/EY | Deliverable | 1 | 2025-05-01 | 2025-05-26 | bar: 2025-05-05 to 2025-05-26
Develop change & training plan to support future process (including Allocations playbook) |  | RTX/EY |  |  | 2025-04-07 | 2025-08-15 | Open | bar: 2025-04-07 to 2025-08-11
| Review current RTX policy materials and update according to final allocation design (e.g., driver definitions, etc.) | RTX | Summary Task | 2 | 2025-07-15 | 2025-08-15 | Open | bar: 2025-07-21 to 2025-08-11
| Consolidate process documentation into Horizon portal and address gaps | EY | Summary Task | 2 | 2025-07-15 | 2025-08-15 | Open | bar: 2025-07-21 to 2025-08-11
| Perform change impact assessment | EY | Summary Task | 2 | 2025-04-07 | 2025-06-02 | Open | bar: 2025-04-07 to 2025-06-02
| Define change initiatives being addressed and engage key stakeholders | EY | Task | 2 | 2025-04-07 | 2025-04-13 | bar: 2025-04-07
| Document current processes as a baseline for change impacts | EY | Task | 2 | 2025-04-13 | 2025-05-01 | bar: 2025-04-14 to 2025-04-28
| Evaluate potential impacts of the change | EY | Task | 2 | 2025-05-01 | 2025-05-15 | bar: 2025-05-05 to 2025-05-12
| Identify potential risks associated with the change initiatives and develop mitigation plan | EY | Task | 2 | 2025-05-01 | 2025-05-15 | bar: 2025-05-05 to 2025-05-12
| Change impact assessment | EY | Deliverable | 2 | 2025-05-01 | 2025-05-19 | bar: 2025-05-05 to 2025-05-19
| Socialize change impacts and risk mitigation plans with stakeholders | EY | Task | 2 | 2025-05-20 | 2025-06-02 | bar: 2025-05-26 to 2025-06-02
| Develop and roll out training materials and plan | RTX | Summary Task | 3 | 2025-06-02 | 2025-08-15 | Open | bar: 2025-06-02 to 2025-08-11
| Training materials developed and plan outlined for training sessions | RTX | Deliverable | 3 | 2025-06-02 | 2025-07-01 | bar: 2025-06-02 to 2025-06-30
Enhance and update Horizon Dashboard |  | RTX |  |  | 2025-06-02 | 2025-08-15 | Open | bar: 2025-06-02 to 2025-08-11
| Develop additional views in Horizon | RTX | Summary Task | 2 | 2025-06-02 | 2025-08-15 | Open | bar: 2025-06-02 to 2025-08-11
| Document detailed Horizon requirements (e.g., executive view, total dollar v. variance, etc.) | EY | Deliverable | 2 | 2025-06-02 | 2025-06-15 | bar: 2025-06-02 to 2025-06-09
| Identify target areas in dashboard for update and upgrade | RTX | Task | 2 | 2025-06-15 | 2025-06-21 | bar: 2025-06-16
| Evaluate potential enhancement options | RTX | Task | 2 | 2025-06-21 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
| Perform update and improvements to Horizon dashboard | RTX | Task | 2 | 2025-06-30 | 2025-08-07 | bar: 2025-06-30 to 2025-08-04
| Communicate updates made and host informational sessions on changes / new abilities of dashboard | RTX | Task | 2 | 2025-08-07 | 2025-08-15 | bar: 2025-08-11
Leverage technology to enable cost allocations process |  | EY |  |  | 2025-05-12 | 2025-11-03 | Open | bar: 2025-05-12 to 2025-11-03
| Explore immediate automation opportunities | EY | Summary Task | 2 | 2025-05-12 | 2025-07-07 | Open | bar: 2025-05-12 to 2025-07-07
| Review existing process to determine which activities may benefit from automation | EY | Task | 2 | 2025-05-12 | 2025-05-18 | bar: 2025-05-12
| Evaluate potential automation solutions and compatibility with existing systems | EY | Task | 2 | 2025-05-19 | 2025-06-01 | bar: 2025-05-19 to 2025-05-26
| Prioritize technology advancements | EY | Task | 2 | 2025-06-02 | 2025-06-23 | bar: 2025-06-02 to 2025-06-23
| Establish high level implementation considerations | EY | Task | 2 | 2025-06-23 | 2025-07-07 | bar: 2025-06-23 to 2025-07-07
| Develop Automation business case and plan for execution | EY | Deliverable | 2 | 2025-06-02 | 2025-07-07 | bar: 2025-06-02 to 2025-07-07
| Define requirements for future cost allocations process | EY | Summary Task | 3 | 2025-06-30 | 2025-09-15 | Open | bar: 2025-06-30 to 2025-09-15
| Review existing technology processes and assess potential technology capabilities and implementations | EY | Task | 3 | 2025-06-30 | 2025-07-14 | bar: 2025-06-30 to 2025-07-14
| Determine requirements needed for technology upgrade | EY | Task | 3 | 2025-07-07 | 2025-07-28 | bar: 2025-07-07 to 2025-07-28
| Defined Allocations tool requirements list | EY | Deliverable | 3 | 2025-07-07 | 2025-07-28 | bar: 2025-07-07 to 2025-07-28
| Create detailed plan of requirements and procedures for selecting / implementing EPM, ERP, etc. | EY | Task | 3 | 2025-08-04 | 2025-09-15 | bar: 2025-08-04 to 2025-09-15
| Perform tool selection across various allocation technology options (e.g., EPM, ERP, point solution) | RTX | Summary Task | 3 | 2025-08-03 | 2025-10-01 | Open | bar: 2025-08-04 to 2025-09-29
| Centralize allocations data including budgets and base data (potential interim solution in tandem to tool decision/implementation) | RTX | Task | 3 | 2025-08-03 | 2025-09-01 | bar: 2025-08-04 to 2025-09-01
| Perform system gap analysis across platforms | RTX | Task | 3 | 2025-08-24 | 2025-10-01 | bar: 2025-08-25 to 2025-09-29
| Identify interim solution pre/post s/4 | RTX | Task | 3 | 2025-09-07 | 2025-10-01 | bar: 2025-09-08 to 2025-09-29
| Implement improved allocation technology and any identified interim solution | EY | Summary Task | 3 | 2025-09-01 | 2025-11-03 | Open | bar: 2025-09-01 to 2025-11-03
| Define clear objectives for the technology implementation | EY | Task | 3 | 2025-09-01 | 2025-09-14 | bar: 2025-09-01 to 2025-09-08
| Create a detailed implementation plan that outlines timelines, milestones, and resource requirements | EY | Task | 3 | 2025-09-01 | 2025-09-21 | bar: 2025-09-01 to 2025-09-15
| Configure and customize the technology | EY | Task | 3 | 2025-09-25 | 2025-10-30 | bar: 2025-09-29 to 2025-10-27
| Develop training materials and conduct training | EY | Task | 3 | 2025-10-30 | 2025-11-03 | bar: 2025-11-03
Socialize changes with RTX and USG (Government Accounting) |  | RTX |  |  | 2025-06-02 | 2025-11-03 | Open | bar: 2025-06-02 to 2025-11-03
| USG socialization plan | RTX | Summary Task | 3 | 2025-06-16 | 2025-10-06 | Open | bar: 2025-06-16 to 2025-10-06
| Develop time phased plan to socialize changes to USG | RTX | Task
| Provide regular updates to DCMA/DCAA related to upcoming changes and timeline | RTX | Task
| Provide formal notification of cost accounting practices no later than 10/31/25 | RTX | Task |  | 2025-10-01 | 2025-10-31 | bar: 2025-10-06 to 2025-10-27
| Develop and execute training and communcations | RTX | Summary Task | 3 | 2025-06-02 | 2025-11-03 | Open | bar: 2025-06-02 to 2025-11-03
| Communicate changes to impacted employees and BU’s | RTX | Task
| Update policies, procedures, and charging guidance based on new drivers | RTX | Task
t | Milestone
 | time axis 2025-02-03 to 2025-12-29
Compile all relevant data related to the non-brochure ES cost structure - move, should be covered in data/tech
Develop and implement recommendations to enhance non-Brochure ES costs and the corresponding process structure - move, this should be tied to future opps around corp allocatiosn
Formulas:
Start = MIN([Start, row below]:F35)
End = MAX([End, row below]:G35)
Note on B54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let’s specify the activities we will be taking on here like we do below. As part of this, we will be developing all leadership materials, including Neil-ready quantitative summaries from detailed cost impacts, regular status updates (including risks/mitigations), etc. This program has a lot of eyes, so the TMO-related activity around executive updates for various forums (e.g., Finance Council, Neil reviews) here is not light.
Note on B98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It might be helpful as we continue to build out the details to add in Milestones or deliverables where it makes sense, likely at the title activity level (Direct charge process design). For example, Develop comprehensive SOPs for direct charge would be an action and a deliverable
Note on C159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this not be RTX? We can advise
Note on C166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this not be RTX? We can advise
Note on F186: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start date depending on fall brochure/forecasts and calculating the allocations that the BU’s will receive
Note on B194: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Direct charge will not have any drivers
Note on B261: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will look very different based on decisions made for which technology will be leveraged; on the roadmap this activity should visually show that (perhaps a dotted line around the chevron)
Note on B266: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These make sense to me

## Project Plan_vRoadmap (3) (hidden)
Raytheon (RTX) Cost Allocations Transformation - Phase 2
Activities | [6 empty] | Month 0 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
[7 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44
 | time axis 2025-02-03 to 2025-12-29
0. Engagement Administration and Economics |  | Owner | Wave | Start | End | Status
1 | Setup engagement in GEAR (incl. upload of SOW and MSA) | EY |  |  |  | Open
2 | Create SQ plan | EY |  |  |  | Open
3 | Review RTX Data Privacy requirements | EY |  |  |  | Open
4 | Update engagement win status | EY |  |  |  | Open
5 | Perform ETC #1 | EY |  |  |  | Open
6 | Execute internal kickoff | EY |  |  |  | Open
7 | Distribute invoice #1 | EY |  |  |  | Open
8 | Perform ETC #2 | EY |  |  |  | Open
9 | Perform ETC #3 | EY |  |  |  | Open
10 | Perform ETC #4 (if needed) | EY |  |  |  | Open
11 | Distribute invoice #2 | EY |  |  |  | Open
Phase 1 Extension |  | Owner |  | Start | End | Status
Define new driver data | [5 empty] | Open
| Create and Facilitate completion of template for new drivers to service owners | EY
| Create data collection template for all proposed drivers (e.g., calculations, level of detail, sources, owners, frequency) and share with service owners | EY |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Create base data catalog - including new data collected, forecast and actuals | EY |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Perform high level analysis of forecast to actuals to confirm predictability hypotheses | EY |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
Finalize and socialize Direct Charge decision Matrix | [5 empty] | Open
Create Direct Charge decision matrix
| Finalize Direct Charge decision matrix |  |  | 2025-02-10 | 2025-02-14 | bar: 2025-02-10
| Evaluate direct charge cost pools with ES Finance (2nd round) |  |  | 2025-02-10 | 2025-02-21 | bar: 2025-02-10 to 2025-02-17
| Evaluate direct charge cost pools with OneRTX and Service Catalog teams |  |  | 2025-02-10 | 2025-02-21 | bar: 2025-02-10 to 2025-02-17
Support Socialization of Allocation Architecture | [5 empty] | Open
| Facilitate detailed reviews with stakeholders | EY
| Evaluate drivers with ES Finance (2nd Round) | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Evaluate drivers and cost pools with Government accounting team | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Evaluate drivers with ES Services owners | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Engage OneRTX team and Service Catalog team on cost categories in order to future proof drivers and pools | EY / RTX |  | 2025-02-17 | 2025-02-28 | bar: 2025-02-17 to 2025-02-24
| Develop agenda and materials for BU outreach - cost pools, drivers, direct charge | EY |  | 2025-02-24 | 2025-02-28 | bar: 2025-02-24
Refine model, perform scenarios | [5 empty] | Open
| Refine high level cost impact model with new driver data | EY
| Iterate model to reflect new driver data | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Iterate model to reflect additional pressure tested scenarios | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Iterate model to reflect direct charge scenarios (omission of costs) | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
| Socialize high level impacts | EY |  | 2025-03-03 | 2025-03-07 | bar: 2025-03-03
TMO |  | Owner |  | Start | End | Status
Engagement Management |  | EY |  | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Transformation Management |  | EY |  | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Critical Path |  | Owner |  | Start | End | Status
Standardize and Streamline ES Cost Allocation Process | [5 empty] | Open
| Direct charge process definition & design | EY | 1 | 2025-03-03 | 2025-04-18 | Open | bar: 2025-03-03 to 2025-04-14
| Map and define the current state direct charge allocation process (SIPOC) | EY
| Define direct charge criteria | EY
| Create direct charge process flows and procedures | EY
Develop comprehensive SOPs and training materials for updated processes
| Non-direct process definition & design | EY | 1 | 2025-04-21 | 2025-07-04 | Open | bar: 2025-04-21 to 2025-06-30
| Map and define the current state non-direct allocation process (SIPOC) | EY
Outline opportunities for standardization and streamlining within process
Test opportunity hypotheses for all non-direct allocations
| Design streamlined process incorporating upstream data collection and downstream reporting | EY
Refine allocation architecture to incorpoate Future ES scope
| Develop comprehensive SOPs and training materials for updated processes | EY
| Model and Implement non-direct charge changes to Brochure | RTX/EY
Host review workshops on final allocation architecture with key finance stakeholders (FPA, Controllership, ES, Gov Acct)
| Streamline upstream/downstream timely distribution to BUs for Non-Direct Process | RTX | 2 | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Identify current process for distribution and submission of brochure
Determine pain points and opportunities with adjustment of brochure distribution
Standardize communication procedures for receiving and submitting of brochure
Socialize standardized process for distribution of brochure to BUs
Re-align on Benchmark cost structure against industry standards and best practices
Examine Internal Orders
Document current and future state data flows | [5 empty] | Open
| Identify driver data sources and level of detail | EY |  | 2025-03-10 | 2025-04-11 | Open | bar: 2025-03-10 to 2025-04-07
Engage key subject matter resources to gather data on allocations requirements
Compile a list of data sources that provide information related to drivers
Assess data availability and accessibility at level of detailed required
Review the collected cost data to identify inconsistencies or discrepancies in how costs are allocated across different services
Develop policies that outline how driver data should be collected, maintained, and reported and specify ownership
Outline and implement processes to regularly monitor compliance with governance policies and data quality standards for driver data sources
| Understand systems landscape and data flows for non-direct ES costs | EY |  | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
Map the current state non-direct charge data flow, illustrating how data is collected, processed and reported
Identify stakeholders involved in non-direct charge data flow
Establish roles for setting policies, reviewing processes, and ensuring adherence to governance standards
Develop policies that outline how non-direct charge data should be collected, processed, stored, and reported and socialize with stakeholders
| Understand systems landscape and data flows for direct ES costs | RTX |  | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
Map the current state direct charge data flow, illustrating how data is collected, processed and reported
Identify stakeholders involved in direct charge data flow
Establish roles for setting policies, reviewing processes, and ensuring adherence to governance standards
Develop policies that outline how direct charge data should be collected, processed, stored, and reported and socialize with stakeholders
| Evaluate opportunities to harness data to optimize ES operational reporting | RTX |  | 2025-07-21 | 2025-10-03 | Open | bar: 2025-07-21 to 2025-09-29
Work with stakeholders to establish KPIs and frequency of reporting
Initiate Horizon improvements aligned to BU feedback (e.g., )
Draft documentation and create reporting templates
Socialize reports with key stakeholders and establish periodic reviews
Execute changes in the system to consolidate cost centers
Conduct a comprehensive review of the current cost center structure and identify areas of consolidation
Expand scope of assessment to include corporate costs (consistency check)
Streamline layers of cost allocation from ES to receiving cost centers |  | EY | 3 |  |  | Open
Identify receiving cost centers and align drivers
| Evaluate driver data to lowest BU cost mapping level | EY
| Evaluate direct charge impact on BUs cost mapping | EY
Review draft cost mapping with ES Finance Leads & BU Leads
Review draft cost mapping with BU leads
Socialize refined driver data to BUs & ES Leads
| Document opportunities to remove layers of cost allocation within CA and PW |  |  |  |  | Open
Workshop new structure with ES functional leads and gather feedback
Workshop new structure with BU leads and gather feedback
Incorporate feedback from current process and develop future state process
Socialize standardized process for distribution of brochure to BUs
| Implement changes for brochure release | RTX
Update CAS statements (Government Accounting) | [5 empty] | Open
| Identify cost accounting changes |  |  | 2025-03-10 | 2025-05-26 | Open | bar: 2025-03-10 to 2025-05-26
Assess existing CHO, ES, IHO, and Segment CAS Disclosure Statements
| Revise CAS disclosure statements |  |  | 2025-06-02 | 2025-10-02 | Open | bar: 2025-06-02 to 2025-09-29
Update existing CHO, ES, IHO, and Segment CAS Disclosure Statements based on new allocation bases/drivers
Prepare forward pricing and provisional billing rate proposals |  |  |  | 2025-08-18 | 2025-10-06 | Open | bar: 2025-08-18 to 2025-10-06
Provide BU’s with updated allocation data
Assist BU’s in the preparation of forward pricing and provisional billing rate proposals, as needed
Direct charge pressure test |  | EY |  | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
Obtain indirect rate models (i.e., incurred cost submissions) and CAS disclosure statements from all segments, CHO’s, and IHO’s
Obtain contract back log/forecast data by cost element
Assess impact to contracts based on contract type.
Assess administrative burden of capturing new drivers
Refine list of new allocation bases/drivers based on financial impacts and data availability; develop time phased plan to implement changes, as needed.
Driver pressure test |  | EY |  | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
Obtain contract back log/forecast data by cost element
Assess impact to contracts based on contract type.
Assess administrative burden of capturing new drivers
Refine list of new allocation bases/drivers based on financial impacts and data availability; develop time phased plan to implement changes, as needed.
Detailed cost impact model and analysis |  | EY |  | 2025-05-02 | 2025-10-14 | Open | bar: 2025-05-05 to 2025-10-13
Based on the list of impacted segments, identify universe of CAS covered contracts
Assess cost impact for each cost accounting practice change
USG socialization plan |  | EY |  | 2025-06-16 | 2025-10-06 | Open | bar: 2025-06-16 to 2025-10-06
Develop time phased plan to socialize changes to USG
Provide regular updates to DCMA/DCAA related to upcoming changes and timeline
Provide formal notification of cost accounting practices no later than 10/31/25
Business Partnering |  | Owner |  | Start | End | Open
Enhance governance around incoming ES scope | [5 empty] | Open
| Document service catalog and cost structure mapping (e.g. cost centers map to which service area) | RTX | 1 | 2025-03-17 | 2025-06-06 | Open | bar: 2025-03-17 to 2025-06-02
Identify target service areas within each mission area
Establish service area mapping of cost pools
Develop documentation of new structure and mapping of cost pools within service areas
| Define guidance and process for incoming ES cost (e.g., OneRTX when are costs allocated v. direct?) | EY | 1 | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
Identify potential scope increases through connectivity with OneRTX team
Map examples of incoming costs to mission and service areas in brochure
Support alignment on landing location of cost (cost pool, driver); modeling to be done by OneRTX team not EY
Use identified examples and basis for guidance and go-forward process for incoming ES cost
| Design improved scope approval process | RTX | 2 |  |  | Open
Understand current scope approval process and shortcomings
Develop recommendations for improvements to process (e.g., workflow, timing, etc.)
Execute improvements to process
| Assess functional ES budget ownership (e.g., HRIS costs - EAS or HR?) |  |  |  |  | Open
Document budget owners for each cost pool within ES scope (brochure and non-brochure)
Establish guiding principles (e.g., functional apps budgets should sit within function itself)
Assess budget ownership and make recommendations where applicable
Develop change & training plan to support future process (including Allocations playbook)
| Review current RTX policy materials and update according to final allocation design (e.g., driver definitions, etc.) | RTX | 2 |  |  | Open
| Consolidate process documentation into Horizon portal and address gaps | EY | 2 |  |  | Open
| Perform change impact assessment | EY | 2 |  |  | Open
Define change initiatives being addressed and engage key stakeholders
Document current processes as a baseline for change impacts
Evaluate potential impacts of the change
Identify potential risks associated with the change initiatives and develop mitigation plan
Socialize change impacts and risk mitigation plans with stakeholders
| Develop and roll out training materials and plan | RTX | 3 |  |  | Open
Enhance and update Horizon Dashboard | [5 empty] | Open
Develop additional views in Horizon
Document detailed requirements (e.g., executive view, total dollar v. variance, etc.)
Identify target areas in dashboard for update and upgrade
Evaluate potential enhancement options
Perform update and improvements to Horizon dashboard
Communicate updates made and host informational sessions on changes / new abilities of dashboard
Leverage technology to enable cost allocations process | [5 empty] | Open
| Explore immediate automation opportunities | EY |  | 2025-09-15 | 2025-10-10 | Open | bar: 2025-09-15 to 2025-10-06
Review existing process to determine which activities may benefit from automation
Evaluate potential automation solutions and compatibility with existing systems
Prioritize technology advancements
Establish high level implementation considerations
| Define requirements for future cost allocations process | EY |  |  |  | Open
Review existing technology processes and assess potential technology capabilities and implementations
Determine requirements needed for technology upgrade
Create detailed plan of requirements and procedures for selecting / implementing EPM, ERP, etc.
| Perform tool selection across various allocation technology options (e.g., EPM, ERP, point solution) | RTX |  | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Centralize allocations data including budgets and base data (potential interim solution in tandem to tool decision/implementation)
Perform system gap analysis across platforms
Identify interim solution pre/post s/4
| Implement improved allocation technology and any identified interim solution | EY |  | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Define clear objectives for the technology implementation
Create a detailed implementation plan that outlines timelines, milestones, and resource requirements
Configure and customize the technology
Develop training materials and conduct training
Develop and execute training and communcations |  |  |  | 2025-06-02 | 2025-12-29 | Open | bar: 2025-06-02 to 2025-12-29
Communicate changes to impacted employees and BU’s
Update policies, procedures, and charging guidance based on new drivers
t | Milestone | bar: 2025-02-24
Compile all relevant data related to the non-brochure ES cost structure - move, should be covered in data/tech
Develop and implement recommendations to enhance non-Brochure ES costs and the corresponding process structure - move, this should be tied to future opps around corp allocations
 | time axis 2025-02-03 to 2025-12-29
Note on B54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let’s specify the activities we will be taking on here like we do below. As part of this, we will be developing all leadership materials, including Neil-ready quantitative summaries from detailed cost impacts, regular status updates (including risks/mitigations), etc. This program has a lot of eyes, so the TMO-related activity around executive updates for various forums (e.g., Finance Council, Neil reviews) here is not light.
Note on B59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It might be helpful as we continue to build out the details to add in Milestones or deliverables where it makes sense, likely at the title activity level (Direct charge process design). For example, Develop comprehensive SOPs for direct charge would be an action and a deliverable
Note on B147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are we exploring opportunities to assess who should own what? E.g., HRIS is owned by Apps currently but could be evaluated are being owned by HR function in future state
Note on B152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On the roadmap, let’s have a dotted line between this chevron and the direct and non direct process chevrons… for example, the direct decision matrix (activity under design direct process) is a component of / will be cited in this more comprehensive ‘guidance’ for incoming cost
Note on B196: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will look very different based on decisions made for which technology will be leveraged; on the roadmap this activity should visually show that (perhaps a dotted line around the chevron)

## Project Plan_v2 (hidden)
Raytheon (RTX) Cost Allocations Transformation - Phase 2
Activities | [5 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
[6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44
 | time axis 2025-03-03 to 2025-12-29
0. Engagement Administration and Economics |  | Owner | Start | End | Status
1 | Setup engagement in GEAR (incl. upload of SOW and MSA) | EY |  |  | Open
2 | Create SQ plan | EY |  |  | Open
3 | Review RTX Data Privacy requirements | EY |  |  | Open
4 | Update engagement win status | EY |  |  | Open
5 | Perform ETC #1 | EY |  |  | Open
6 | Execute internal kickoff | EY |  |  | Open
7 | Distribute invoice #1 | EY |  |  | Open
8 | Perform ETC #2 | EY |  |  | Open
9 | Perform ETC #3 | EY |  |  | Open
10 | Perform ETC #4 (if needed) | EY |  |  | Open
11 | Distribute invoice #2 | EY |  |  | Open
TMO |  | Owner | Start | End | Status
Engagement Management |  | EY | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Transformation Management |  | EY | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Process |  |  |  |  | Status
Allocation Process |  |  |  |  | Open
| Direct charge process definition & design | EY | 2025-03-03 | 2025-04-18 | Open | bar: 2025-03-03 to 2025-03-31
| Map the current state direct charge allocation process (SIPOC) | EY
| Define direct charge criteria | EY
| Identify areas for streamlining process | EY
| Create direct charge documentation and procedures | EY
| Implement direct charge changes to Brochure | RTX/EY
| Non-direct process definition & design | EY | 2025-04-21 | 2025-07-04 | Open | bar: 2025-04-21 to 2025-06-30
| Map the current state non-direct allocation process (SIPOC) | EY
| Design streamlined process incorporating upstream data collection and downstream reporting | EY
| Create non-direct charge documentation and procedures | EY
| Implement direct charge changes to Brochure | RTX/EY
| Define key performance indicators to measure the effectiveness and timeliness of the new processes | EY
| Streamline upstream/downstream timely distribution to BUs | RTX | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Identify current process for distribution and submission of brochure
Determine pain points and opportunities with adjustment of brochure distribution
Standardize communication procedures for receiving and submitting of brochure
Socialize standardized process for distribution of brochure to BUs
| Implement distribution changes for brochure release | RTX
| Standardize process of selecting allocation for added ES Costs | EY | 2025-06-09 | 2025-08-15 | Open | bar: 2025-06-09 to 2025-08-11
Identify current allocation methodology framework
Establish standard practices for determining allocation methodologies
Create documentation and structure for selecting cost drivers
Socialize new framework with ES functional / BU leads
| Develop and socialize data collection process and reporting | EY | 2025-05-05 | 2025-08-01 | Open | bar: 2025-05-05 to 2025-07-28
Identify data needs (sources, frequency, level of detail)
Establish data standards to ensure consistency and accuracy in data collection
Design data collection process and timeline, identifying necessary tools
Design standardized reporting templates that facilitate clear and consistent presentation of data
Socialize the data collection process and reporting framework to stakeholders
ES Cost Structure |  |  |  |  | Open
| Document service catalog and cost structure mapping (e.g. cost centers map to which service area) | RTX | 2025-03-17 | 2025-06-06 | Open | bar: 2025-03-17 to 2025-06-02
Identify target service areas within each mission area
Establish service area mapping of cost pools
Develop documentation of new structure and mapping of cost pools within service areas
Socialize new structure with ES functional leads
| Assess non-brochure ES cost structure for consistency (e.g., Apps pool) | EY |  |  | Open
Compile all relevant data related to the non-brochure ES cost structure
Review the collected cost data to identify inconsistencies or discrepancies in how costs are allocated across different services
Benchmark cost structure against industry standards and best practices
Document inconsistencies and assess their overall impacts
Develop and implement recommendations to enhance non-Brochure ES cost structure
| Streamline consolidation and maintanence of cost centers | RTX | 2025-08-18 | 2025-10-31 | Open | bar: 2025-08-18 to 2025-10-27
Conduct a comprehensive review of the current cost center structure and identify areas of improvement
Develop standardized guidelines for establishing, consolidating, and maintaining cost centers; including guidelines for when new cost centers are added to the ES Brochure
Socialize new structure with ES stakeholders and outlines roles / responsibilities for maintaing cost centers
Develop documentation of cost center guidelines and maintenance and implement periodic reviews
Future Cost Additions to Brochure
| Identify and map costs not in brochure today | EY | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
| Identify costs not in brochure today with potential to be included | EY
| Map costs to mission and service areas in brochure | EY
| Align with RTX on potential for costs to be added to brochure | RTX/EY
| Communicate opportunties of future cost additions in brochure | EY
Business Partnering |  |  |  |  | Open
| Define governance / framework around incoming ES costs (e.g., OneRTX - when are costs allocated v. direct?) | EY |  |  | Open
Establish a governance structure, including roles / responsibilities of stakeholders involved in the governance of incoming ES costs
Define cost allocation criteria and guidelines for when costs should be direct vs. in the ES Brochure
Develop reference materials and train stakeholders on governance structure and framework
| Develop budget ownership catalog to assist with direct charging (ES. V. BUs), functional budgets (EAS v. HR for functional apps), cost center ownership, etc. | EY |  |  | Open
Define budget types and work with key stakeholders to understand current ownership
Develop clear guidelines that define ownership for each budget category, including roles and responsibilities for budget management, approval processes, and reporting requirements
Document guidelines and ownership catalog and socialize with stakeholders
| Change impact assessment | EY | 2025-07-07 | 2025-08-29 | Open | bar: 2025-07-07 to 2025-08-25
Define change initiatives being addressed and engage key stakeholders
Document current processes as a baseline for change impacts
Evaluate potential impacts of the change
Identify potential risks associated with the change initiatives and develop mitigation plan
Socialize change impacts and risk mitigation plans with stakeholders
Future Cost Additions to Brochure
| Identify and map costs not in brochure today | EY | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
| Identify costs not in brochure today with potential to be included | EY
| Map costs to mission and service areas in brochure | EY
| Align with RTX on potential for costs to be added to brochure | RTX/EY
| Communicate opportunties of future cost additions in brochure | EY
Adds - CM
Establish flexible allocations process that incorporates increased future ES scope
Document current scope approval process and design improved process - governance
Create allocations playbook that includes updated process flows, handoffs and criteria for future allocations to accommodate ES growth - governance
Develop comprehensive SOPs and training materials for any updated processes (e.g., direct charge) - governance
Expand scope of assessment to include corporate costs (consistency check)- cost structure / target state design
Host review workshops on final allocation architecture with key finance stakeholders (FPA, Controllership, ES, Gov Acct) - cost structure / target state design
Backlog re-prioritization; define practical next steps on implementation/sprint plan; support near term improvements - add regular milestones for thisevery 8 weeks
Engage key subject matter resources to gather data on allocations requirements, validate findings, verify assumptions, and test hypotheses on streamlining allocations - cost structure / target state design
Identify unique considerations / impacts on allocations (e.g., tax) - cost structure / target state design
Test drivers based on statistical relationships (actuals v. forecast) - cost structure / target state design
Data / Tech |  |  |  |  | Status
Governance |  |  |  |  | Open
x | Direct charge data flow | EY | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
x
x
x
x | Non-direct charge data flow | EY | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
x
x
x
x | Identify driver data sources and level of detail | EY | 2025-03-10 | 2025-04-11 | Open | bar: 2025-03-10 to 2025-04-07
x
x
x
x | Evaluate data to support ES operational reporting | EY | 2025-07-21 | 2025-10-03 | Open | bar: 2025-07-21 to 2025-09-08; 2025-09-29
x
x
x
| Enhance communication channels and POCs | EY | 2025-08-04 | 2025-10-03 | Open | bar: 2025-08-04 to 2025-09-29
x
x
x
Placeholder for Government Accounting |  |  |  |  | Open
| Detailed cost impact modeling (example) | EY | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
x
x
x
Technology Advancements |  |  |  |  | Open
| Explore automation opportunities | EY | 2025-09-15 | 2025-10-10 | Open | bar: 2025-09-29 to 2025-10-06
x
x
x
| Assess allocation technology options - EPM, ERP, point solution | EY | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
x
x
x
| Implement data collection and allocation technology | EY | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
x
x
x
Adds - CM
Document upstream and downstream data flow - data and systems mapping
Identify rules / existing logic and opportunities to streamline (reduce rules) - base data maintenance and preparation
Initiate Horizon improvements aligned to BU feedback (e.g., ) - data / reporting
Centralize allocations data including budgets and base data (potential interim solution in tandem to tool decision/implementation) - data / reporting
perform system gap analysis across platforms - data and systems mapping
Identify interim solution pre/post s/4 - data and systems mapping
t | Milestone
 | time axis 2025-03-03 to 2025-12-29
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can we build out the activities beneath all of our top level chrvrons? For example in order to define the process, we will need to map out the current process (e.g., SIPOC), identify areas for streamlining, and then build the new process
Note on B48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agree - is this part of non-direct process above though?
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need this?
Note on B77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let’s understand the EY-related activities for this; I would imagine that this is something RTX would take on rather than us. Glad we have it noted here.
Note on B146: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What do we mean by this
Note on B152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tech?
Note on B165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will look very different based on decisions made for which technology will be leveraged; on the roadmap this activity should visually show that (perhaps a dotted line around the chevron)

## Project Plan_v1 (2) (hidden)
Raytheon (RTX) Cost Allocations Transformation - Phase 2
Activities | [5 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
[6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44
 | time axis 2025-03-03 to 2025-12-29
0. Engagement Administration and Economics |  | Owner | Start | End | Status
1 | Setup engagement in GEAR (incl. upload of SOW and MSA) | EY |  |  | Open
2 | Create SQ plan | EY |  |  | Open
3 | Review RTX Data Privacy requirements | EY |  |  | Open
4 | Update engagement win status | EY |  |  | Open
5 | Perform ETC #1 | EY |  |  | Open
6 | Execute internal kickoff | EY |  |  | Open
7 | Distribute invoice #1 | EY |  |  | Open
8 | Perform ETC #2 | EY |  |  | Open
9 | Perform ETC #3 | EY |  |  | Open
10 | Perform ETC #4 (if needed) | EY |  |  | Open
11 | Distribute invoice #2 | EY |  |  | Open
TMO |  | Owner | Start | End | Status
Engagement Management |  | EY | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Transformation Management |  | EY | 2025-03-03 | 2025-11-24 | Open | bar: 2025-03-03 to 2025-11-24
Open
Open
Process |  |  |  |  | Status
Allocation Process |  |  |  |  | Open
Map the current state allocation process (SIPOC)
Identify areas for streamlining process
| Direct charge process definition & design | EY | 2025-03-03 | 2025-04-18 | Open | bar: 2025-03-03 to 2025-03-31
| Non-direct process definition & design | EY | 2025-04-21 | 2025-07-04 | Open | bar: 2025-04-21 to 2025-06-30
| Streamline upstream/downstream timely distribution to BUs | EY | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
| Standardize allocation methodology | EY | 2025-06-09 | 2025-08-15 | Open | bar: 2025-06-09 to 2025-08-11
Build new allocations process
ES Cost Structure |  |  |  |  | Open
| Service catalog and cost structure mapping | EY | 2025-03-17 | 2025-06-06 | Open | bar: 2025-03-17 to 2025-06-02
Assess non-brochure ES cost structure for consistency (e.g., Apps pool)
| Identify and map costs not in brochure today | EY | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
| Streamline consolidation and maintanence of cost centers | EY | 2025-08-18 | 2025-10-31 | Open | bar: 2025-08-18 to 2025-10-27
Business Partnering |  |  |  |  | Open
Define governance / framework around incoming ES costs (e.g., OneRTX - when are costs allocated v. direct?)
Develop budget ownership catalog to assist with direct charging (ES. V. BUs), functional budgets (EAS v. HR for functional apps), cost center ownership, etc.
| Change impact assessment | EY | 2025-07-07 | 2025-08-29 | Open | bar: 2025-07-07 to 2025-08-25
Costs Not in Brochure Today
Data / Tech |  |  |  |  | Status
Governance |  |  |  |  | Open
| Direct charge data flow | EY | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
| Non-direct charge data flow | EY | 2025-03-03 | 2025-05-02 | Open | bar: 2025-03-03 to 2025-04-28
| Identify driver data sources and level of detail | EY | 2025-03-10 | 2025-04-11 | Open | bar: 2025-03-10 to 2025-04-07
| Develop and socialize data collection process and reporting | EY | 2025-05-05 | 2025-08-01 | Open | bar: 2025-05-05 to 2025-07-28
| Evaluate data to support ES operational reporting | EY | 2025-07-21 | 2025-10-03 | Open | bar: 2025-07-21 to 2025-09-08; 2025-09-29
| Enhance communication channels and POCs | EY | 2025-08-04 | 2025-10-03 | Open | bar: 2025-08-04 to 2025-09-29
BU Impact Analysis |  |  |  |  | Open
| Identify allocation engine and provide modeling requirements | EY | 2025-03-17 | 2025-05-02 | Open | bar: 2025-03-17 to 2025-04-28
| Impact Modeling | EY | 2025-04-14 | 2025-08-01 | Open | bar: 2025-04-14 to 2025-07-28
Technology Advancements |  |  |  |  | Open
| Explore automation opportunities | EY | 2025-09-15 | 2025-10-10 | Open | bar: 2025-09-29 to 2025-10-06
| Assess allocation technology options - EPM, ERP, point solution | EY | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
| Implement data collection and allocation technology | EY | 2025-11-03 | 2025-12-29 | Open | bar: 2025-11-03 to 2025-12-29
Government Accounting |  |  |  |  | Status
| Driver change cost impact analysis | EY | 2025-03-03 | 2025-06-06 | Open | bar: 2025-03-03 to 2025-06-02
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
t | Milestone
 | time axis 2025-03-03 to 2025-12-29
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can we build out the activities beneath all of our top level chrvrons? For example in order to define the process, we will need to map out the current process (e.g., SIPOC), identify areas for streamlining, and then build the new process
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agree - is this part of non-direct process above though?
Note on B45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What do we mean by this?
Note on B48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need this?
Note on B50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Category - costs not in brochure today
Note on B51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let’s understand the EY-related activities for this; I would imagine that this is something RTX would take on rather than us. Glad we have it noted here.
Note on B59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Business partnership rather than process
Note on B72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: process
Note on B75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What do we mean by this
Note on B79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tech?
Note on B80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How is this diff than gov impact model?
Note on B87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gov accounting activity