## Task Orchestration Template
Process | Task | Dependency | Owner | Due Date | Status | Comments
AP | Post vendor invoices | None | AP Team | Day -1 | Pending
AP | Run accruals | Invoice posting | AP Lead | Day +1 | Pending
AR | Apply customer receipts | Invoices posted | AR Team | Day +1 | Pending
Payroll | Post payroll JEs | Payroll run completed | HR/Payroll | Day 0 | Pending
GL | Run depreciation | FA upload complete | FA Team | Day +1 | Pending
GL | Intercompany eliminations | Sub-ledger postings complete | GL Lead | Day +3 | Pending
Consolidation | Run consolidation | GL tasks complete | Finance Consolidation | Day +4 | Pending
Reporting | Release FS | Consolidation complete | CFO Office | Day +5 | Pending

## ERP Upload Template
Task ID | Task Name | Process | Start Date | End Date | Dependency Task ID | Owner | Auto/Manual | Escalation Contact
1001 | Post Vendor Invoices | AP | 29th | 30th | None | AP Manager | Manual | Controller
1002 | Run AP Accruals | AP | 1st | 1st | 1001 | AP Lead | Auto | Controller
2001 | Apply Customer Payments | AR | 1st | 1st | 1001 | AR Manager | Manual | Finance Head
3001 | Payroll Journal Posting | Payroll | 30th | 0th | None | Payroll Lead | Auto | HR Head
4001 | Depreciation Run | FA | 1st | 1st | 1002 | FA Manager | Auto | Controller
5001 | Consolidation Run | GL | 3rd | 4th | 4001 | GL Manager | Auto | CFO